## Sheet1
Module | Sub-Components / Features | Development Effort (Days) | Testing Effort (QA & UAT) (Days) | Total Effort (Days) | Already Done (Reduce Efforts)
1. Authentication & User Management | Login, JWT Authentication, RBAC, User Management, Password Reset | 6 days | 03 days | 9 days
2. AI Voice Interview Engine | Voice interaction, STT/TTS integration, Interview flow, AI conversation management | 18 days | 6 days | 22-25 days | Speech to text, voice interaction, face detection, AI based Evaluation (Soheb) (3 days )
3. Technical Assessment Engine | Dynamic question generation, Coding/MCQ evaluation, Scoring logic, Adaptive interviews | 14 days | 04 days | 18 days
4. RAG Knowledge Base | Document upload, Embedding generation, Vector DB, Context retrieval, Knowledge management | 10 days | 04 days | 14-18 days
5. AI Evaluation & Report Generation | Candidate analysis, Skill scoring, Strengths/Weaknesses, Interview summary, Recommendation | 9 days | 04-5 days | 12 days
6. Anti-Cheating & Security | Tab switching detection, Audio monitoring, Identity validation, Audit logs | 08 days | 04 days | 12 days | Multi face detection , long pauses, tab swittching
7. Dashboard & Analytics | Recruiter dashboard, Candidate reports, Analytics, Charts, Interview history | 08 days | 03 days | 11 days
8. ATS/HRMS Integration & Notifications | Applicant Tracking System integration, Email notifications, Calendar scheduling, APIs, Webhooks | 07 days | 03 days | 10 days
9. Admin Panel & System Settings | Prompt management, AI model configuration, User roles, System settings, Logs | 06 days | 03 days | 09 days
10. Deployment | Docker, Cloud deployment, Environment setup, Monitoring, Production release | 05 days | 02 days | 07 days
Total Estimated Effort |  | 62- 91 Days | 28- 38 Days | 90-129 days